## 16-Week Schedule
Task | Owner | Critical path? | Depends on | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | W14 | W15 | W16 | Notes
Lease signed / kickoff | Owner | YES | —
Survey / as-builts | Designer | YES | Kickoff
Concept / fixture plan | Designer | YES | Survey
Permit drawings | GC / designer | YES | Concept
Permit issue | AHJ | YES — CONTROLS PATH | Permit drawings
Long-lead millwork PO | Owner | YES — CONTROLS PATH | Approved drawings
Fixture RFQ + award | Owner | YES | Fixture plan
Fixture production | Supplier | YES | Approved shop drawings
Utility / MEP rough-in | GC | YES | Permit issue
Utility connection | Utility / GC | YES — CONTROLS PATH | Rough-in
Finishes | GC |  | MEP rough-in
Fixture delivery | Supplier | YES | Production
Fixture install | Installer | YES | Finishes + delivery
Lighting / signage | Trades |  | Finishes
Punch list | GC + owner |  | Install
Open | Owner | YES | Punch criticals closed

## Critical Path Notes
Mark permit issue, long-lead millwork, and utility connection as controlling. Slippage there moves open day.